## Overview
INTELLIGENT ADAPTIVE LEARNING PLATFORM
Numerical Analysis & Scientific Computing - Project Steering Plan
PROJECT FACT SHEET
Project title | Intelligent Adaptive Learning Platform for Numerical Analysis and Scientific Computing
Student | Yassine Ben Nessib
Supervisor | Afif Beji, MSc
School | ESPRIT School of Engineering
Type | Final Year Project (PFE) - 6-month internship
Methodology | Agile / Scrum - 13 two-week sprints
Start / End | February 28, 2026 -> August 22, 2026 (26 weeks)

## Gantt Chart
GANTT CHART - 26-Week Schedule
Student: Yassine Ben Nessib ¦ Supervisor: Afif Beji, Civil Engineer ¦ ESPRIT 2026
PHASE | TASK | SPRINT | PRIO. | W1 28/02 | W2 07/03 | W3 14/03 | W4 21/03 | W5 28/03 | W6 04/04 | W7 11/04 | W8 18/04 | W9 25/04 | W10 02/05 | W11 09/05 | W12 16/05 | W13 23/05 | W14 30/05 | W15 06/06 | W16 13/06 | W17 20/06 | W18 27/06 | W19 04/07 | W20 11/07 | W21 18/07 | W22 25/07 | W23 01/08 | W24 08/08 | W25 15/08 | W26 22/08
Phase 1 Setup & Foundations | T1 - Research & state of the art | S1 | Must
| T2 - Database design (Neo4j + PostgreSQL) | S2 | Must
| T3 - Infrastructure & DevOps (Docker, CI/CD) | S3 | Must
| T4 - Implementation & initial graph population | S4 | Must
Phase 2 Core Features | T5 - Adaptive assessment & profiling | S5 | Must
| T6 - Graph extension & multi-level content | S6 | Must
| T7 - AI tutoring with RAG (GraphRAG) | S7 | Must
| T8 - Visualization & interactive tools (Manim) | S8 | Must
Phase 3 Logic & Front-end | T9 - Remediation intelligence & algorithms | S9 | Must
| T10 - UI & analytics | S4-S10 | Must
Phase 4 Evaluation & Defense | T12 - Experimental study & data collection | S12 | Should
| T13 - Statistical analysis & comparison | S13 | Should
Cross-cutting (continuous) | T11 - Testing & reliability | S4-S11 | Must
| T14 - Writing & dissemination (report, paper) | S10-S13 | Must
| T15 - User study preparation | S5-S11 | Must

## Agile Sprints
AGILE BACKLOG - 13 TWO-WEEK SPRINTS
Sprint | Period | Sprint goal | Main tasks | Sprint deliverable
Sprint 1 | W1-2 (Feb 28 - Mar 13) | Research & scoping | Literature review (knowledge graphs, LLMs, cognitive load); GraphRAG benchmark | Literature synthesis
Sprint 2 | W3-4 (Mar 14 - Mar 27) | Data design | Neo4j schema (Concept, Prerequisite, Module, Resource); PostgreSQL schema | Validated data model
Sprint 3 | W5-6 (Mar 28 - Apr 10) | Infrastructure & DevOps | docker-compose; GitHub Actions CI/CD; bcrypt + JWT authentication | Operational DevOps environment
Sprint 4 | W7-8 (Apr 11 - Apr 24) | Functional baseline | FastAPI APIs (auth, profiles); graph population (Interpolation, Integration, ODEs) | Baseline prototype
Sprint 5 | W9-10 (Apr 25 - May 8) | Adaptive assessment | Diagnostic question bank; N->N-1 progression algorithm; competency profiling | Adaptive assessment engine
Sprint 6 | W11-12 (May 9 - May 22) | Pedagogical content | Complete graph for 3 modules; dynamic sequencing; multi-level content | Complete knowledge graph
Sprint 7 | W13-14 (May 23 - Jun 5) | AI tutoring | RAG pipeline (LangChain); GraphRAG; prompt engineering; SymPy validation | Functional AI tutor
Sprint 8 | W15-16 (Jun 6 - Jun 19) | Visualization | Manim animations; JSXGraph/Desmos integration | Multi-modal library
Sprint 9 | W17-18 (Jun 20 - Jul 3) | Intelligent remediation | Error classification; targeted remediation; 'best next node' algorithm | Remediation engine
Sprint 10 | W19-20 (Jul 4 - Jul 17) | UI & analytics | Mastery dashboards; API optimization; UI finalization | Production-grade UI
Sprint 11 | W21-22 (Jul 18 - Jul 31) | Testing & freeze | Mathematical correctness tests; load tests; UX audit; feature freeze | Prototype ready for user study
Sprint 12 | W23-24 (Aug 1 - Aug 14) | Experimental study | Pre-test / post-test; 25-30 students; log collection; surveys & interviews | Experimental data
Sprint 13 | W25-26 (Aug 15 - Aug 28) | Analysis & dissemination | Statistical analysis; PFE report + paper writing; defense preparation | Report, paper, defense

## Risks
RISK REGISTER
# | Risk | Probability | Impact | Level | Mitigation plan
1 | Scope too large for one person in six months | High | High | Critical | Prioritize with MoSCoW; user study + paper = 'Should'. Scope decision point at milestone M2 (Sprint 8).
2 | User study scheduled too late | High | High | Critical | Start recruitment, ethics approval, and control group definition as early as Sprint 5.
3 | AI (LLM) hallucination | High | High | Critical | GraphRAG to ground answers; SymPy/NumPy calculation validation; strict system prompts.
4 | No slack / buffer in the schedule | High | Medium | High | Keep a reserve in Sprint 13; if late at Sprint 8, reduce scope (modules, animations).
5 | Course content authoring load (3 versions x 3 modules) | Medium | High | High | Reuse the supervisor's course as base corpus; start writing as early as Sprint 6.
6 | Frontend choice inconsistency | Medium | Medium | Medium | Lock the frontend decision early and keep it consistent across all project documents.
7 | LLM API costs (GPT-4 / Claude / Gemini) | Medium | Medium | Medium | Define a budget; cache responses; plan a cheaper fallback model.
8 | Manim animation production time | Medium | Medium | Medium | Limit to 3-4 key animations; script and render early.
9 | Neo4j graph complexity & performance | Medium | Medium | Medium | Optimize Neo4j indexes; load-test sequencing queries from Sprint 6 onward.
10 | Low adoption / insufficient student recruitment | Medium | High | High | Intuitive UX; recruit early; plan a backup sample; participation incentives.